## Excel Gantt Chart Template
Excel Gantt Chart Template
Enter Your Project Details Here |  |  | DURATION (days)
START DATE | END DATE | DESCRIPTION
2019-04-02 | 2019-04-07 | 요구사항 추출(시나리오) | 5
2019-04-07 | 2019-04-13 | 요구사항 분석(UML) | 6
2019-04-10 | 2019-04-16 | 요구사항 명세(명세서) | 6
2019-04-13 | 2019-04-16 | 요구사항 검증 | 3
2019-04-16 | 2019-04-18 | 프로젝트 팀 구성 | 2
2019-04-19 | 2019-04-24 | 스케줄링(WBS) | 5
2019-04-19 | 2019-04-30 | 비용산정 | 11
2019-04-26 | 2019-04-30 | 일정 계획(Gantt) | 4
2019-04-27 | 2019-06-18 | 프로젝트 통제(EVM) | 51
2019-04-30 | 2019-05-14 | 서버 설계 | 14
2019-04-30 | 2019-05-14 | UI 설계 | 14
2019-04-30 | 2019-05-14 | 알고리즘 설계 | 14
2019-04-30 | 2019-05-14 | 데이터 구조 설계 | 14
2019-05-14 | 2019-05-28 | 서버 개발(AWS) | 14
2019-05-14 | 2019-05-21 | UI개발(안드로이드) | 7
2019-05-21 | 2019-06-04 | 기능 개발(Java) | 13
2019-05-14 | 2019-06-04 | 매뉴얼 개발 | 20
2019-06-04 | 2019-06-07 | 단위 테스트 | 3
2019-06-07 | 2019-06-11 | 통합 테스트 | 4
2019-06-04 | 2019-06-11 | 테스트 결과 보고서 | 7
2019-06-11 | 2019-06-18 | 유지보수 | 7
Make impressive PowerPoint Gantt charts for important meetings. |  |  |  | Instantly turn Excel data into PowerPoint slides with the Office Timeline add-in for PowerPoint.
www.officetimeline.com
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download the Free Office Timeline plug-in for PowerPoint - 14-day Trial Edition.
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of
PowerPoint. Copy your Excel table and paste it into Office Timeline with the PASTE button.
3. Click the green SAVE button to instantly produce a PowerPoint Gantt chart slide.

## Sheet1
2019-04-02 | 2019-04-16

## Excel Timeline Template
Excel Timeline Template
Enter Your Project Details Here
DATE | DESCRIPTION | POSITION
2018-05-10 | Kick Off | 1
2018-06-07 | Milestone 1 | 2
2018-07-21 | Milestone 2 | 1
2018-08-01 | Checkpoint A | 4
2018-09-20 | Milestone 3 | 3
2018-10-30 | Milestone 4 | 2
2018-12-20 | Checkpoint B | 3
2019-01-30 | Milestone 5 | 4
2019-02-10 | Milestone 6 | 1
2019-03-30 | Milestone 7 | 2 |  | `
2019-05-20 | Checkpoint C | 3
2019-05-30 | Sign Off | 1
Make beautiful timelines in PowerPoint for important meetings. |  |  | Instantly turn Excel data into PowerPoint slides with the Office Timeline add-in for PowerPoint.
www.officetimeline.com
https://www.officetimeline.com/download
Note on D6: Excel Project Timeline Tip: The position values vary the height of your Milestones and are used to prevent text overlap. Using negative numbers will place Milestones labels below the timeband. If you position a Milestone below the timeband click on its label in the chart to set its Label Position to below.
Note on B17: Excel Project Timeline Tip: To add more Milestones, insert new rows into this table and then use the Select Data field to update your Series as shown in step # 3 here: https://www.officetimeline.com/make-timeline/excel
3 Easy steps to instantly turn Excel data into a PowerPoint slide
1. Download the Free Office Timeline plug-in for PowerPoint - 14-day Free Trial.
2. Open PowerPoint and click on NEW Timeline from the Office Timeline tab inside of PowerPoint.
Copy your Excel table and paste it into Office Timeline with the PASTE button.
3. Click the green SAVE button to instantly produce your timeline slide.